## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Siri Sri | 2026-04-09 | Duplicate chunks were created when the same project document was uploaded multiple times. | 1 | Siri Sri | Maintainability | Added duplicate chunk checking before rebuilding the FAISS index. | 2026-02-09 | Closed | Verified with repeated uploads.
2 | Siri Sri | 2026-04-09 | Question search failed when the knowledge base was not available. | 1 | Siri Sri | Logical | Added validation for missing FAISS index and chunks file. | 2026-02-09 | Closed | Error message is displayed correctly
3 | Siri Sri | 2026-04-09 | Source document name was not available with retrieved chunks. | 1 | Siri Sri | Data Error | Added source filename with every stored document chunk. | 2026-03-09 | Closed | Source is displayed with search results.
4 | Siri Sri | 2026-04-09 | Upload interface supported only one document at a time. | 1 | Siri Sri | User Interface | Updated Flask upload handling to support multiple file uploads. | 2026-03-09 | Closed
5 | Siri Sri | 2026-04-09 | Generated uploads and knowledge-base files could be added to Git repository. | 1 | Siri Sri | Configuration | Added uploads/ and knowledge_base/ to .gitignore and removed them from Git tracking. | 2026-03-09 | Closed | Runtime files are excluded from GitHub
6 | Siri Sri | 16/09/2026 | DOCX milestone tables were not extracted by the document loader, causing milestone information to be missing from the agent context. | 2 | Siri Sri | Data Extraction | Updated DOCX loader to extract both paragraphs and table contents. | 16/09/2026 | Closed | Verified with project plan containing milestone table.
7 | Siri Sri | 16/09/2026 | Scope Extraction Agent returned an empty responsibilities list even when responsibility information was present in the retrieved context. | 2 | Siri Sri | Logical | Updated scope extraction prompt and tested responsibility extraction with project documents. | 16/09/2026 | closed | Requires additional validation with multiple documents.
8 | Siri Sri | 16/09/2026 | Blocker Agent incorrectly classified the final project deadline as a pending decision. | 2 | Siri Sri | Logical | Strengthened pending-decision rules to accept only explicitly unresolved decisions. | 16/09/2026 | closed | Further testing required to prevent incorrect classification.
9 | Siri Sri | 16/09/2026 | Blocker Agent inferred a due date for an action item from a milestone date instead of using an explicitly stated action-item due date. | 2 | Siri Sri | Logical | Updated agent instructions to avoid inventing or inferring action-item due dates. | 16/09/2026 | closed | Validate using meeting-notes documents.
10 | Siri Sri | 16/09/2026 | Local Ollama LLM response generation was significantly slower than the previously used OpenAI API. | 2 | Siri Sri | Performance | Migrated LLM execution from OpenAI API to local Ollama after API credits were exhausted. Performance optimization is pending. | 16/09/2026 | closed | Local model provides usable responses but requires optimization.
11 | Siri Sri | 23/09/2026 | Agent routing returned an incorrect agent for some project queries. | 3 | Siri Sri | Logical | Updated routing rules to improve query classification. | 24/09/2026 | Closed | Verified with scope, risk and blocker queries.
12 | Siri Sri | 24/09/2026 | Conversational assistant did not retain context for follow-up questions. | 3 | Siri Sri | Logical | Added conversation context handling for follow-up queries. | 26/09/2026 | Closed | Tested with multiple related questions.
13 | Siri Sri | 24/09/2026 | React frontend did not display backend error responses clearly. | 3 | Siri Sri | User Interface | Added frontend error handling and user-friendly error messages. | 26/09/2026 | Closed | Verified API failure handling.
14 | Siri Sri | 24/09/2026 | Multiple document queries returned incomplete retrieved context. | 3 | Siri Sri | Data Retrieval | Improved multi-document retrieval and context handling. | 27/09/2026 | Closed | Verified using multiple project documents.
15 | Siri Sri | 25/09/2026 | Conversational assistant generated unsupported responses for unavailable information. | 3 | Siri Sri | Logical | Strengthened source-grounding and unavailable-information handling. | 28/09/2026 | Closed | Verified with questions outside project context.
| Siri Sri | 2026-05-10 | Dashboard health score was not displayed correctly when project analysis data was unavailable. | 4 | Siri Sri | Logical | Added validation and fallback handling for missing project health data. | 2026-06-10 | Closed | Verified dashboard behavior when health score data is missing.
| Siri Sri | 2026-06-10 | Dashboard did not display all extracted risks and action items from the project documents. | 4 | Siri Sri | Data Retrieval | Updated dashboard integration to retrieve and display risk and action item results. | 2026-07-10 | Closed | Verified displayed results against agent outputs.
| Siri Sri | 2026-07-10 | Uploading new meeting notes did not update the knowledge base correctly. | 4 | Siri Sri | Data Extraction | Updated incremental ingestion handling to process newly uploaded documents. | 2026-08-10 | Closed | Tested with new meeting notes and progress updates.
| Siri Sri | 2026-08-10 | Repeated document uploads created duplicate chunks in the knowledge base. | 4 | Siri Sri | Data Integrity | Added duplicate checking before storing new document chunks. | 2026-09-10 | Closed | Verified repeated uploads do not create duplicate entries.
| Siri Sri | 2026-09-10 | CSV and DOCX documents produced inconsistent extracted content during end-to-end testing. | 4 | Siri Sri | Data Extraction | Improved document parsing validation and tested extracted content across supported file types. | 2026-10-10 | Closed | Validated extraction using PDF, DOCX, TXT, and CSV files.
| Siri Sri | 2026-10-10 | Conversational assistant returned unsupported information when project context was unavailable. | 4 | Siri Sri | Logical | Improved retrieval-context validation and handling of unavailable information. | 2026-11-10 | Closed | Tested questions both inside and outside the available project context.
| Siri Sri | 2026-11-10 | Technical documentation did not reflect the latest dashboard and incremental upload features. | 4 | Siri Sri | Documentation | Updated the technical documentation and project report to match the implemented features. | 2026-12-10 | Closed | Reviewed documentation against the current application.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others